## KYC_Portal
|  |  |  | WCF Methods & Complexity |  |  | WebAPI Methods |  |  | WebAPI DEV | WebAPI DEV | NG-APP DEV |  |  | NG-APP DEV | NG-APP DEV
# | Folder/SubFolder | PageName | Actions count | simple | moderate | complex | Count | Complexity | Dependency | Notes | Status | UI | Actions | Dependency | Notes | Status
1 | Popup | Comments | 2 |  |  |  | 0 | - | many | No need of API | addressed |  |  |  | No need of API
2 | Popup | ConfirmationMessageBox | 4 |  |  |  | 0 | - | few | No need of API | addressed |  |  |  | No need of API
3 | Popup | CrossBroderActivity | 3 | 3 |  |  | 3 | moderate | many | Validation are there | Completed
4 | Popup | DatagridPopup |  |  |  |  | 0 |  |  | No need of API | addressed |  |  |  | No need of UI
5 | Popup | RSALogin | 2 |  | 1 |  | 1 | moderate
6 | UserControls\MainTab | CrossBorderTabUC |  | 2 |  |  | 1 | simple | few | 2way | Completed
7 | UserControls | AddressUC | 6 | 2 |  |  | 0 | moderate | few | 1way | addressed
8 | UserControls | BindingNavigator | 6 | 3 |  |  | 0 | - | few | No need of API | addressed
9 | UserControls | BindingNavigatorNew |  |  |  |  | - | - | - | Not in use | addressed |  |  |  | No need of UI
10 | UserControls | CIPInfo | 3 | 4 |  |  | 1 | moderate | few | Validation are there | Completed
11 | UserControls | CIPMultiple | 1 | 2 |  |  | 1 | simple | few | Validation are there | Completed
12 | UserControls | CrossBorderActivityReviewUC |  | 1 |  |  | 0 | - |  | No need of API | addressed
13 | UserControls | CustomerINfoUC |  | 2 |  |  | 0 | moderate |  | 1way | addressed
14 | UserControls | DocumentsUC |  | 4 |  |  | 0 | moderate |  | 1way | addressed
15 | UserControls | ExpectedActivity | 7 | 3 |  |  | 2 | simple | many | 2way | Completed
16 | UserControls | MainDetlsUC | 2 | 3 |  |  | 2 | moderate | many | 2way | Completed
17 | UserControls | NegativeNewsUC |  | 1 |  |  | 0 | simple |  | 1way | Completed
18 | UserControls | OtherUC |  | 1 |  |  | 0 | simple |  | 1way | Completed
19 | UserControls | OwnershipDirectorsUC |  | 1 |  |  | 0 | simple |  | 1way | Completed
20 | UserControls | SLN | 2 | 3 |  |  | 1 | moderate | few | 2way | Completed
21 |  | App |  |  |  |  | 0 | simple |  | 1way | Completed
22 |  | Comments | 2 |  |  |  | 0 | - |  | No need of API | addressed
23 |  | Home | 1 | 2 |  |  | 0 | - | many | Same implementation as Main | addressed |  |  |  | No need of UI
24 |  | Home1 |  | 1 |  |  | - | - | - | Not in use | addressed |  |  |  | No need of UI
25 |  | Main | 4 | 5 |  |  | 3 | moderate | many | Completed 3 API methods | Completed
26 |  | NewRequestDetails | 5 | 6 |  |  | 3 | moderate | many | Completed 3 API methods | Completed
27 |  | RequestWindow | 3 | 12 |  |  | 3 | moderate | many | 2way | Completed
|  |  |  | 61 | 1 | 0 | 21 |  |  | % Completed | 96% |  |  |  | % Completed | 0%

## Sheet2
approach
1. validation information
2. rsa check
3. export excel
| # | Features | StatusCode
| 1 | Address
| 2 | CIPInfo
| 3 | CIPMultiple | 1way
| 4 | Comments | 1way
| 5 | CrossBroderActivity
| 6 | CustomerInfo
| 7 | Documents | 1way
| 8 | EditRequestDetails
| 9 | ExpectedActivity
| 10 | MainDetails
| 11 | NegativeNews | 1way
| 12 | NewRequestDetails
| 13 | Other | 1way
| 14 | OwnershipDirectors | 1way
| 15 | RSALogin
| 16 | Search-Entity | 2way